## Sheet1
| RWA Vendor Admin App Status |  | 8 Section/28 section Completed App Size 22 MB |  |  | Last Updated (21 December 2020)
No | Section | Subsection | Subsubsection | App Side Coding (UI+Backend) Status | Api Design Status | Api Integration | Time
1 | Dashboard | Block Wise Summary |  | Completed | Completed | Completed
|  | EC Users |  | Completed | Completed | Completed
|  | Cam Bills Summary | O/s Summary | Completed | Completed | Completed
|  |  | CAM Bills Summary | Completed | Completed | Completed
|  |  | Summary | Completed | Completed | Completed
2 | User Management | Customer Management | Customer List | Completed | Completed | Completed
|  |  | User Status change | Completed | Completed | Completed
|  |  | Admin Status change | Completed | Completed | Completed
|  |  | Edit | Completed | Completed | Completed
|  |  | Delete | Completed | Completed | Completed
|  |  | Add Customer | Completed | Completed | Completed
|  | Membership Applications | Pending Admin Approval List | Completed | Completed | Completed
|  |  | Add Membership Applications | Completed | Completed | Completed
|  |  | Pending President/ Secretary (Office Bearers) Approval List | Completed | Completed | Completed
|  |  | Pending ID Cards List | Completed | Completed | Completed
|  |  | ID Cards Issued List | Completed | Completed | Completed
|  |  | Sent For Correction List | Completed | Completed | Completed
|  |  | Rejected Applications List | Completed | Completed | Completed
|  |  | Pending Admin Approval Edit | Completed | Completed | Completed
|  |  | Pending Admin pdf generation and Print | Completed
|  |  | Pending President/ Secretary (Office Bearers) Approval Edit | Completed | In Progess | In Progess | 2hrs
|  |  | Pending President/ Secretary (Office Bearers) Approval pdf generation and Print | Pending | Pending | Pending
|  |  | Pending ID Cards Edit | Completed | Completed | Completed
|  |  | Pending ID Cards pdf generation and Print | Pending | Pending | Pending
|  |  | ID Cards Issued pdf generation and Print | Pending | Pending | Pending
|  |  | Sent For Correction Edit | Completed | Completed | Completed | 3 hrs
|  |  | Sent For Correction pdf generation and Print | Pending | Pending | Pending
|  | Send Username And Password | Customer List | Completed | Completed | Completed
|  |  | Send Username and Password email | Completed | Completed | Completed
3 | Billing | Billing Management | Bill List | Completed | Completed | Completed
|  |  | View Bill | Completed | Completed | Completed
|  |  | Generate Bill PDF | Pending | Pending | Pending
|  |  | Send SMS And Email | Completed | Completed | Completed
|  |  | Edit | Completed | Completed | Completed
|  | Payment Management | Edit | Completed | Completed | Completed
|  |  | Delete | Completed | Completed | Completed
4 | Documents | Document Management | Document List | Completed | Completed | Completed
|  |  | Edit | Completed | Completed | Completed
|  |  | Delete | Completed | Completed | Completed
|  |  | Search | Completed | Completed | Completed
|  |  | Status Change | Completed | Completed | Completed
|  |  | Add Document | Completed | Completed | Completed
|  | Covid Document Management | Covid Document List | Completed | Completed | Completed
|  |  | Edit | Completed | Completed | Completed
|  |  | Delete | Completed | Completed | Completed
|  |  | Search | Completed | Completed | Completed
|  |  | Status Change | Completed | Completed | Completed
|  |  | Add Document | Completed | Completed | Completed
|  |  | Approve Documents | Completed | Completed | Completed
|  | Grocery Document Management | Grocery Document List | Completed | Completed | Completed
|  |  | Add Grocery Item | Completed | Completed | Completed
|  | Doctors Document Management | Doctors Document List | Completed | Completed | Completed
5 | Blocks | Block Management | Block List | Completed | Completed | Completed
|  |  | Edit | Completed | Completed | Completed
|  |  | Delete | Completed | Completed | Completed
|  |  | Search | Completed | Completed | Completed
|  |  | Status Change | Completed | Completed | Completed
|  |  | Add block | Completed | Completed | Completed
6 | Buy And Sell | Properties | Properties List | Completed | Completed | Completed
|  |  | Status Change | Completed | Completed | Completed
|  |  | Search | Completed | Completed | Completed
7 | Complaints | Manage Complaints | Complaints List | Completed | Completed | Completed
|  |  | Search | Completed | Completed | Completed
|  |  | Allot Subadmin | Completed | Completed | Completed
|  |  | Add remark (Resolve) | Completed | Completed | Completed
|  | Manage Category | Category List | Completed | Completed | Completed
|  |  | Add Category | Completed | Completed | Completed
|  |  | Search | Completed | Completed | Completed
|  |  | Remove Category | Completed | Completed | Completed
|  |  | Status Change | Completed | Completed | Completed
|  | Manage Sub Category | Sub Category List | Completed | Completed | Completed
|  |  | Add Sub Category | Completed | Completed | Completed
|  |  | Search | Completed | Completed | Completed
|  |  | Remove Sub Category | Completed | Completed | Completed
|  |  | Status Change | Completed | Completed | Completed
|  | Manage Subadmin | Subadmin List | Completed | Completed | Completed
|  |  | Add Sub Admin | Completed | Completed | Completed
|  |  | Search | Completed | Completed | Completed
|  |  | Remove Subadmin | Completed | Completed | Completed
8 | Advertisements | Add/Manage Advertise | Advertise List | Completed | Completed | Completed
|  |  | Edit | Completed | Completed | Completed
|  |  | Delete | Completed | Completed | Completed
|  |  | Search | Completed | Completed | Completed
|  |  | Status Change | Completed | Completed | Completed
|  | Add/Manage Category | Edit |  |  |  | 5 hrs
|  |  | Delete |  |  |  | 2 hrs
|  | Pricing Table Management | Edit |  |  |  | 5 hrs
|  |  | Delete |  |  |  | 2 hrs
|  | CMS Management - Terms & Conditions | Edit |  |  |  | 3 hrs
|  |  | Delete |  |  |  | 2 hrs
9 | Highlight Events | Highlight Events | Add View Update | Completed | Completed | Completed
10 | Mailer | Send Custom mail to multiple users |  |  |  |  | 8 hrs T 48
|  | Send mail to multiple users |  |  |  |  | 8 hrs T
11 | Notice Board | Add/Manage Notice | Notice Lists |  |  |  | 3 hrs
|  |  | Post Notice |  |  |  | 4 hrs
|  |  | Edit |  |  |  | 3 hrs
|  |  | Delete |  |  |  | 2 hrs
|  |  | Status Change |  |  |  | 3 hrs
12 | Home Slider |  | Slider List |  |  |  | 3 hrs
|  |  | Add Slider |  |  |  | 4 hrs
|  |  | Edit |  |  |  | 3 hrs
|  |  | Delete |  |  |  | 2 hrs
|  |  | Status Change |  |  |  | 2hrs
13 | Events |  | Events List
|  |  | Edit |  |  |  | 3 hrs
|  |  | Delete |  |  |  | 3 hrs 99
|  |  | search |  |  |  | 2 hrs
|  |  | Status Change |  |  |  | 2hrs
|  |  | Add Events |  |  |  | 4 hrs
|  |  | Sell Tickets |  |  |  | 4 hrs
14 | HSD Reports | Report Management | EXECUTIVE SUMMARY REPORT |  |  |  | 10-12 hr
15 | News Papers | Add/Manage News Papers | News List |  |  |  | 3 hrs
|  |  | Edit |  |  |  | 4 hrs
|  |  | Delete |  |  |  | 2 hrs
|  |  | Status Change |  |  |  | 2hrs
|  |  | Search |  |  |  | 2 hrs
|  |  | Add News Papers |  |  |  | 5 hrs
|  | Newspaper Bills Management | News Paper Bill list |  |  |  | 3 hrs
|  |  | Add news paper bill |  |  |  | 5-6 hrs
16 | Task Tracker | Assign /Update Task | Task List |  |  |  | 4 hrs
|  |  | Add Task |  |  |  | 5 hrs
|  |  | Status Change |  |  |  | 2 hrs
|  | View Update Task | Task List |  |  |  | 2 hrs
|  | Form Request | Form Lists |  |  |  | 4 hrs
|  |  | Search |  |  |  | 3 hrs
|  |  | Status Change |  |  |  | 2 hrs
|  |  | Add Email |  |  |  | 6 hrs
17 | Good Samaritans |  | Samaritans List |  |  |  | 4 hrs
|  |  | Status Change |  |  |  | 2 hrs
18 | Manage Google forms | Approval Request |  |  |  |  | 4 hrs
|  | Removal Requests |  |  |  |  | 4 hrs
19 | Amenities Management | Amenities Management | Amenities Lists |  |  |  | 4 hrs
|  |  | Edit |  |  |  | 3hrs 100
|  |  | Delete |  |  |  | 2 hrs
|  |  | Status Change |  |  |  | 2 hrs
|  |  | Add Amenities |  |  |  | 4 hrs
20 | Bazzar | Add/Manage Category | Cateogory List |  |  |  | 3 hrs
|  |  | Category filter |  |  |  | 2 hrs
|  |  | Add Cateogory |  |  |  | 3 hrs
|  |  | Edit |  |  |  | 3 hrs
|  |  | Delete |  |  |  | 2 hrs
|  |  | Status Change |  |  |  | 2 hrs
|  | Add/Manage Subcategory | Sub Category List |  |  |  | 3 hrs
|  |  | SubCategory filter |  |  |  | 2 hrs
|  |  | Add SubCateogory |  |  |  | 4 hrs
|  |  | Edit |  |  |  | 3 hrs
|  |  | Delete |  |  |  | 2 hrs
|  |  | Status Change |  |  |  | 3 hrs
|  | Add/Manage Bazzar | Bazzar List |  |  |  | 3 hrs
|  |  | List filter |  |  |  | 2 hrs
|  |  | Add Service Listing |  |  |  | 5 hrs
|  |  | Edit |  |  |  | 3 hrs
|  |  | Delete |  |  |  | 2 hrs
|  |  | Status Change |  |  |  | 2hrs
21 | Teams | Add/Manage Teams | Teams List |  |  |  | 3 hrs
|  |  | List filter |  |  |  | 2 hrs
|  |  | Add Teams Listing |  |  |  | 4 hrs
|  |  | Edit |  |  |  | 3 hrs
|  |  | Delete |  |  |  | 2 hrs
|  |  | Status Change |  |  |  | 2hrs
22 | Ec Management | Add/Manage ECs Management | ECs List |  |  |  | 3 hrs
|  |  | List filter |  |  |  | 2 hrs
|  |  | Add Ecs Listing |  |  |  | 4 hrs
|  |  | Edit |  |  |  | 3 hrs
|  |  | Delete |  |  |  | 2 hrs
|  |  | Status Change |  |  |  | 2 hrs
23 | CMS | About Us | Add About |  |  |  | 4 hrs
|  | Medical Service | Add Medical Services |  |  |  | 4 hrs
|  |  | View Medical Service |  |  |  | 3 hrs 99
|  | Discussion Foram | Add Discussion Foram |  |  |  | 4 hrs
|  |  | View Discussion Foram |  |  |  | 2 hrs
|  | Privacy policy | Add Privacy & Policy |  |  |  | 3 hrs
|  |  | View Privacy & Policy |  |  |  | 2 hrs
|  | Terms and conditions | Add Terms & Conditions |  |  |  | 3 hrs
|  |  | View Terms & Conditions |  |  |  | 2 hrs
|  | Cookies policy | AddCookies Policy |  |  |  | 2 hrs
|  |  | View Cookies Policy |  |  |  | 3 hrs
|  | contribute | Add Contribute |  |  |  | 2 hrs
|  |  | View Contribute |  |  |  | 2 hrs
|  | Advertise | Add Advertise |  |  |  | 3 hrs
|  |  | View Advertise |  |  |  | 3 hrs
24 | Surveys | Add/Manage Surveys | Survey List |  |  |  | 3 hrs
|  |  | Edit |  |  |  | 3 hrs
|  |  | Delete |  |  |  | 2 hrs
|  |  | Download |  |  |  | 5 hrs
|  |  | Status Change |  |  |  | 2 hrs
|  | Add/Manage Survey result | Survey result List |  |  |  | 3 hrs
|  |  | Edit |  |  |  | 3 hrs
|  |  | Delete |  |  |  | 2 hrs
|  |  | Download |  |  |  | 4 hrs
|  |  | Status Change |  |  |  | 3 hrs
25 | Sales Management | Upload Data /Send | Dynamice Messaging View |  |  |  | 4 hrs
|  |  | Add Dynamice Messaging |  |  |  | 4 hrs
|  | ViewLeads | SALES REPORT List |  |  |  | 4 hrs
26 | Vendor Admin | Add Sub Vendor | Admin & Permissions |  |  |  | 8 hrs
|  | Send Vendor DEtails | Send Username and Password |  |  |  | 5 hrs
|  | Manage Sub Vendor | Admin & Permissions |  |  |  | 4 hrs
|  | RWA Membership | Memebership Status |  |  |  | 4 hrs
|  |  | Update Membership |  |  |  | 5 hrs
27 | Advertise Requests | Advertise Request Management | Advertise Lists |  |  |  | 4 hrs
28 | Construction NoC | List of Sites Under Construction | Sites Under Construction List |  |  |  | 4 hrs
|  |  | View Applications |  |  |  | 3 hrs
|  | Completed Total Task = 87/ 203 |  |  |  |  | Estimate Time Taken = 346 hrs or 2 months